## Sheet1
Weeks (Work 15hrs/week)
Stage | S&M | D&Ms | R | Task | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | Status
Preparetion | / | / | / | Background reading | [31 empty] | √
| / | D1 | / | Lab induction, risk assessment forms and proposal | [31 empty] | √
| S1,S4,S5 | / | / | Learn the theory of the required hardware (FBG,PPG) | [31 empty] | √
| S6,S8 | / | / | Learn the theory of the required software (Labview)
| / | Ms1 | / | Complete introduction part for Final Year Report
Hardware | S1&M1 | D2 | R1,2,3 | Build Windkessel mode and test the seal first (Use two connections together)
| S2&M2 | / | / | Build TIA circuit and test on breadboard first
| S3&M3 | / | R5 | Build Low pass filter circuit and test on breadboard first
| S4&M4 | D3 | R4 | Test the overall PPG sensor (Test individual modules first)
| S5&M5 | D4 | R6,7 | Build FBG sensor and amplify signal with cantilever (Use two types materials )
| S5&M5 | / | / | Stretch:Optimise cantilever to improve signal amplication
| / | Ms2 | / | Complete hardware part for Final Year Report
Software | S6&M6 | D5 | R8,10 | Acquire PPG signal by NI and LabVIEW (Or use Rasberry Pi)
| S7&M7 | D6&Ms3 | R9 | Acquire FBG signal by interrogator
| S8&M8 | D7&Ms4 | R11 | Use Matlab to to draw the distribution for FBG and PPG (Or use LabVIEW directly)
| S8&M8 | / | / | Stretch: Use machine learning to analysis data
| / | D8&Ms5 | / | Complete the overall Final Year Report
Deliverables (D) |  |  |  |  | D1: A proposal about the overview, requirements, methods, risk assessment and time plan of the project. | [30 empty] | √
D2: A Windkessel model that simulates the flow of arteries in the human body under different conditions.
D3: A PPG sensor consists of a photoelectric module, a TIA circuit, and a low pass filter circuit.
D4: An FBG sensor and a cantilever that amplifies its signal.
D5: A LabVIEW programming file can get PPG data.
D6: Acquired files of PPG and FBG data.
D7: A code file on Matlab capable of analysing data from different motion scenarios.
D8: A final year report and some transcripts of experimental procedures.
Milestones (Ms) |  |  |  |  | Ms1: Accomplish all the preparation, including background reading, literature review and datasheet obtaining. | [30 empty] | √
Ms2: Complete hardware design. (Windkessel Model, PPG and FBG sensors).
Ms3: Acquire the measured PPG, FBG data and package it into files.
Ms4: Successfully analysing and comparing data measured by PPG and FBG under different motions.
Ms5: Finish final year report (Thesis).
Exam Period
Winter Holiday
Spring Holiday